Onboarding Process and Implementation Timeline:

|  | Timeline | Notes |
| --- | --- | --- |
| Kick-off meeting at Amazon office in London or SC office in Barcelona | Last week April |  |
| Finalising scaling plan in line with agreed objectives | Last week April | Starting from large cities in the UK, Germany and France. |
| Finalising driver evaluation criteria / algorithm | Last week April | See here for the current driver evaluation criteria and the algorithm behind. |
| In-house team allocation | Last week April | See the Organisational Chart proposed. |
| In-country team allocation | Last week April | See the Organisational Chart proposed. |
| Existing Tech Review: Finalising any additional platform features (including any required API integration) | From May | Post pilot review |
| Existing Tech Review: Finalising any additional dashboard needs | From May | Post pilot review |
| Tech development starts (in case of additional needs) | From May |  |
| Tech development ends (in case of additional needs) | By end May |  |
| Service Club finalising the list of any additional local partners | By end May |  |
| Local partner procurement practice (Capacity, trainer profile approval, insurances, policies, financial health, site visits, agreement of SLA and other procurement related checks) | May | Intention is to select those local partners with nationwide coverage (Lead Suppliers) where possible in order to reduce the number of suppliers involved. Pleased to say that all 9 local partners from the Pilot expressed interest to continue with Service Club, some of which will take on the service nationally. |
| Service Club finalising agreements with local partners based on the agreed scaling plan | May |  |
| All local partner contracts are signed | By end May |  |
| Local partners set up as Suppliers at Service Club platform and finance systems | By end May |  |
| Forecasts vs Partner trainer analysis | By end May |  |
| Introduction and induction of Service Club’s own certified trainers to the project based on the needs outlined in the Forecasts vs Partner trainer analysis | By end May |  |
| Amazon to send theory content to Service Club | After contract signing |  |
| BTW content creation starts | After contract signing | If additional content is required post pilot |
| BTW content deliberations with Amazon | Ongoing May |  |
| BTW content finalised (English) | By mid May |  |
| Content translation (other languages) | By end May |  |
| Distribution of content to partner schools (BTW and Theory) | By end May |  |
| Setting up Language Line account | By end May |  |
| Marketing material creation (hardcopy and videos) | Updated by end May | Already created for 9 countries in local languages. Will require updating (including adding Language Line details). Registration guidelines with QR codes, contact details and communication channels, curriculum, feedback forms to name a few. Please see the relevant section in this RFP for more information. |
| Marketing material approval | By end May |  |
| Distribution of all marketing material to training sites | June |  |
| Creation of Partner School Guidelines | First 2 weeks of May (this is mostly done for the Pilot and will require updating) | Introduction of their Service Club point of contacts Business/training objectives Service Club company culture Project specifications Reminder of the SLA Session start-end times Driver registration Content (BTW) Content (Theory) Vehicles specs Signage Lunch breaks* Driver evaluation with deadlines Driver surveys Use of marketing material Use of Language Line Use of Babel Dispute resolution and escalation Reporting requirements Important policies in Equal Opportunities and Health and Safety, Any other timelines and deadlines FAQs (the list is not exhaustive) * not included to Cargo Bike training |
| Distribution of Partner School Guidelines | From end May |  |
| Local partner meetings / workshops start | On-going from June | A team of 8 business managers and in-country coordinators (UK, Germany and France only) will be conducting individual and group meetings with local partners in order to ensure utmost alignment and standardisation. |
| Trainer training reinforcement in each city (in-person) | From June | Business/training objectives, Service Club company culture, session start-end times, driver registration, content (BTW), content (Theory), vehicles, signage, lunch breaks, driver evaluation with, driver surveys, use of marketing material, use of Language Line, use of Babel… |
| In-person field and classroom inspections by Service Club local teams | From June |  |
| Amazon to provide Service Club with the full list of DSPs in each country | April post contract signing |  |
| Amazon to send DSPs an introductory email introducing Service Club | April - May |  |
| DSP mass survey to obtain any missing information needed to set them up as Clients | May |  |
| Pre-kick off DSP workshops in each country | May - June | Most significant DSPs will be invited from each country to discuss their specific problems and training requirements |
| Registration and onboarding of DSPs at Service Club Platform | June | 90+ DSPs onboarded already during Pilot. |
| Distribution of DSP marketing material | June | Introduction of their Service Club point of contacts, business/training objectives, facilities, curriculum, evaluation, feedback collection, communication channels, meetings, reporting |
| Distribution of DSP training material | June |  |
| DSP individual meetings and workshops start (From largest to the smallest) | June |  |
| Other supplier negotiations (shuttles, catering, training equipment etc…) | On-going from May |  |
| Daily Huddle with Amazon PoC(s) | Ongoing | Ongoing |
| Weekly partner school site visits | From July | First month |
| Monthly/Quarterly partner school site visits | From August | After first month |
| DSP weekly meetings | From July | First 3 months |
| DSP monthly meetings | From August | After first month |