Our unique learnings from our Amazon BTW Pilot

that no other supplier has and our planned actions in Round 2

| Area of improvement | Proposed solution(s) |
| --- | --- |
| Leakage from the morning app training to Service Club BTW training | Lack of sufficient promotion, drivers finishing the app training in different times and lack of waiting areas in some stations were reasons for the leakage. Doing both morning session and the afternoon session together in our facilities will overcome this issue. This way each driver can move straight to BTW training as soon as they complete the app training. In some cities where training cities and classrooms may not be in the same facility, then Service Club will provide a shuttle service to the BTW training for those drivers who finished the morning theory session. Moreover, Service Club working closely with DSPs to encourage them for the training will also increase attendance dramatically. We are devising various incentive schemes for DSPs’ participation including discounted use Service Club’s driver acquisition tools. |
| Attendance forecasting. Same day cancellations of sessions, wasted resources | While not much can be done for an unexpected lack of attendance from drivers, the following actions can reduce the number of last minute cancellations considerably: > Giving Service Club direct contact details of the DSPs. The aim here would be to work together with them to make more accurate forecasts based on their hiring efforts and seasonal changes. If need be, Service Club can also assist the DSP in finding suitable drivers. > Service Club working with its own trainers instead of fully relying on partner school trainers will also introduce a new layer of flexibility if and when forecasts don’t match reality. |
| Sudden change of training days | Service Club working with its own trainers instead of fully relying on partner school trainers will introduce a new layer of flexibility if and when training days have to change suddenly. |
| Communication between Service Club project managers and in-territory Amazon staff members | Service Club to create an onboarding session for each Amazon in-territory staff member for them to fully adopt Service Club’s driver safety training. Service Club will offer the following for seamless communication: - Amazon staff’s onboarding video - Chime - Direct telephone access (Mobile & Cloudtalk) - Email - Whatsapp - Live chat - Feedback forms - Monthly in person meetings with Service Club’s local account manager and Amazon’s local staff to assess and optimise performance. |
| Accurate vehicle type | We have found availability of accurate type of vehicles from one week to the next difficult. For a 12 month contract, we will be able to lease the vehicles annually and leave them at the school premises permanently. |
| Ensuring the driver’s engagement throughout the 4 hours BTW training | Our new interactive content is now heavier on the practical training and have additions that don’t only target accidents and damage but also increase engagement of the trainees. In this new content, we propose each driver to spend 1 hour of their 4 hour BTW training on actual roads. These routes will be selected with public safety in mind. We will also work with the 1 vehicle x 1 trainer x 4 trainees ratio in every country and city involved. |
| DSP / Driver unwillingness to attend | Service Club will regularly promote the training program at DSP level. Local Service Club business managers, in-country coordinators, booking/help desk managers and a call centre will work directly with the DSPs to promote the benefits of taking this opportunity as well as developing incentive programs for each. Service Club will share with Amazon the best practices of how to achieve high attendance in all countries in order to have a standardised approach. Local Service Club business managers will be present in sessions regularly to give onsite training to Amazon local staff to promote the BTW training. Optional: Service Club proposes to give training to the drivers of large DSPs in their own facilities. All equipment to be provided by Service Club. This way, not only we can achieve close to 100% attendance but also allow the DSPs to see the training provided first hand and even contribute to its ever evolving and improving content. A true 3-way partnership can only happen with all parties fully connected and collaborating. |
| Shuttle delays | While the requirement for shuttles may be minimal if the training fields and classrooms are in the same facility, we are aware that this may not be possible in every facility. If shuttles will be needed, in this Round 2, we will make annual arrangements with shuttle companies to ensure a reliable service. We will apply a 3 strikes rule with the shuttle companies we have an arrangement with. 3 lateness will result with termination of our agreement. |
| Drivers' inability to travel between the morning app session (theory) and afternoon BTW session | We will either aim to have the training fields and classrooms in the same facility or shuttles will be hired for the whole day and do return journeys back to the stations. |
| Further standardisation of content | In this round, we will fully micromanage the content. We are already in the process of creating the content that will be used in every single school. The content will be available for schools in all the languages required. Schools will be provided a DOs and DON’Ts guide and will be trained on how to present the content. In this DOs and DON’Ts guide, we will cover everything from the number of cones and road signs to be used through to the colour of any print outs given. Moreover, Service Club working with its own trainers in most locations instead of fully relying on partner school trainers will introduce a new layer of standardisation and micro-manageability. |
| Content further supporting business objectives | Another reason we will be micromanaging the content is to make sure that it covers all of Amazon’s business objectives such as: - Reducing accidents and incidents - Reducing vehicle damage - Increasing driver and public safety - Increasing drivers’ job satisfaction - Removing any stigmas around driver/courier/delivery jobs and ensuring that the trainees see being a drivers as a career - Drivers as Amazon’s brand representatives - Amazon becoming the company that offers the safest environment for its drivers - Positive press on Amazon’s driver quality, driver and public safety measures and reputation We would be happy to discuss further business objectives with Amazon. |
| Venue signage | We will standardise the venue signages and provide them to the schools ourselves. Our local Account Managers will decide where the signage will be placed and will regularly check that they are maintained. |
| BTW training field distance | These three options will be used all together depending on the location and the DSPs: - Classroom and training field in the same facility - Classroom and training field in 15 min proximity with complementary shuttle service in between - Training to be given to the drivers of large DSPs in their own facilities. All equipment to be provided by Service Club. |
| Driver registration problems with the platform, drivers with empty phone batteries, drivers who do not know their DSPs, drivers who do not know their own phone numbers, drivers who do not have email addresses [yes, we have seen it all!] | Training over 170k of our own drivers and almost 500 of Amazon’s, it’s safe to say that we have seen it all and we know how to deal with these issues with patience, empathy and more importantly fast and effective methods. Some of them are: - A 30-second video explaining the registration process will be created and played prior to each morning session. The video will also be on our website. The video will also be sent to the DSPs. - Live chat feature will be created in the registration form for the drivers to get access to our technical team instantly. - Phone charging stations will be available in every classroom. - We will collect the list of attendees with their telephone numbers from each DSP in the morning to advise those drivers who do not know their DSPs or phone numbers. - For those drivers who can not register because they do not have an email address, we have two options: we will either register them with telephone number only or our classroom supervisor will help them obtain a gmail or Hotmail email address on the spot. |
| Unrecognised DSPs in the dashboard | DSP name entry will not be a manual process; DSP names will be pre-populated in a drop-down menu. We will collect the list of attendees from each DSP in the morning to advise those drivers who do not know their DSPs or phone numbers. |
| Speed in creating new dashboard and other tech solutions, bugs | Managed by a Product Owner, a tech team of 2 product managers, 2 developers and one data engineer will be assigned to the project. We will also create a “staging platform” for the BTW platform where new features will be tested before being pushed live. Nevertheless, Amazon and Service Club will agree an SLA for creation of new features in the Service Club platform. |
| Lunch time arrangements | During the pilot, our lunch arrangements were adhoc. For the future contract [Van Driver BTW only], annual agreements will be made with local catering companies. |
| Foreign language requirements of immigrant drivers | For those foreign languages that are expected, we will endeavour to make foreign language trainers available. We will also create a Language Line account and have access to instant video or telephone interpreters in each session. This way, we will be able to cover up to 240+ languages in each session. In every other case, we have now created a How to Use Babel guide. We will soon turn this guide into a video as well. All Service Club trainers will be trained on how to use Babel in a training environment. |
| Berlin slow to adopt Service Club BTW training | Out of the 9 countries we have done the pilot in, Berlin is the only country that was slow to adopt the training. Although the attendance level increased towards the end, with the new contract, we will give extra emphasis to Germany’s implementation, staff training and Service Club-DSP relationships. A local Service Club Account Manager will make a detailed implementation plan which will require weekly visits to each station to optimise processes. |